## Sheet1
ONAP Deployment on Openshift - Issue tracker
Component | Pod name | Error description | Resolutions/Status
Log |  | Failed to apply default image tag "/onap/oom/readiness:3.0.1": couldn't parse image reference "/onap/oom/readiness:3.0.1": invalid reference format | in progress
|  | 0/23 nodes are available: 23 pod has unbound immediate PersistentVolumeClaims. | in progress
|  | Failed to apply default image tag "/onap/oom/readiness:3.0.1": couldn't parse image reference "/onap/oom/readiness:3.0.1": invalid reference format | in progress
SO | so-so-vnfm-adapter | CrashLoopBackOff - issue observed with truststore | in progress
| so-so-etsi-nfvo-ns-lcm | CrashLoopBackOff - issue observed with truststore | in progress
| so-so-monitoring | unmountVolume.SetUp failed for volume "aaf-agent-certs" : configmap "so-cert-wrapper-certs" not found Unable to attach or mount volumes: unmounted volumes=[aaf-agent-certs], unattached volumes=[default-token-sfq9d so-so-monitoring-cert-init-aaf-config aaf-agent-certs aaf-add-config so-monitoring-msb-certificate logs config]: timed out waiting for the condition | in progress
AAF |  | chown: /opt/app/aaf: No such file or directory Readiness probe failed: dial tcp 10.131.43.233:8096: connect: connection refused | in progress
| aaf-aaf-sms | MountVolume.SetUp failed for volume "aaf-agent-certs" : configmap "aaf-cert-wrapper-certs" not found Unable to attach or mount volumes: unmounted volumes=[aaf-agent-certs], unattached volumes=[aaf-agent-certs aaf-add-config aaf-aaf-sms-int-certs aaf-aaf-sms-auth aaf-sms sa-anyuid-token-ssqk4 aaf-aaf-sms-aaf-config]: timed out waiting for the condition | renamed aaf-cert-wrapper-certs to cert-cert-wrapper-certs. Now it's waiting for sms-vault to be ready
| aaf-aaf-sms-vault | unable to set CAP_SETFCAP effective capability: Operation not permitted | in progress
| aaf-aaf-sms-quorumclient | INFO: 2021/04/16 08:53:34 quorumclient.go:77: Starting Log for Quorum Client WARNING: 2021/04/16 08:53:34 quorumclient.go:100: Unable to find a shard file. Registering with SMS... ERROR: 2021/04/16 08:53:34 auth.go:226: Read from file: open auth/aaf-aaf-sms-quorumclient-1/shard: no such file or directory ERROR: 2021/04/16 08:53:34 quorumclient.go:99: Read Shard: open auth/aaf-aaf-sms-quorumclient-1/shard: no such file or directory 2021/04/16 08:53:34 Error while reading CA file open /quorumclient/certs/aaf_root_ca.cer: no such file or directory | in progress
portal | policy-policy-api | Failed to pull image "image-registry.openshift-image-registry.svc:5000/pltf-onap/readiness:3.0.1": rpc error: code = Unknown desc = Error reading manifest 3.0.1 in image-registry.openshift-image-registry.svc:5000/pltf-onap/readiness: unauthorized: authentication required | in progress
| portal-portal-app | INFO - portal-portal-db-config has not succeeded yet | in progress
| portal-portal-cassandra | Readiness probe failed: command timed out Liveness probe failed: command timed out | in progress
| portal-portal-db-config | Failed to pull image "image-registry.openshift-image-registry.svc:5000/pltf-onap/readiness:3.0.1": rpc error: code = Unknown desc = Error reading manifest 3.0.1 in image-registry.openshift-image-registry.svc:5000/pltf-onap/readiness: unauthorized: authentication required | in progress
| portal-portal-widget | Deployment portal-portal-db is NOT ready Failed to pull image "dibi/envsubst": rpc error: code = Unknown desc = Error reading manifest latest in docker.io/dibi/envsubst: toomanyrequests: You have reached your pull rate limit. You may increase the limit by authenticating and upgrading: https://www.docker.com/increase-rate-limit | in progress
| portal-portal-db | Failed to apply default image tag "/": couldn't parse image reference "/": invalid reference format | in progress
sdc | sdc-sdc-be | No subject alternative DNS name matching aaf-locate.pltf-onap found. | in progress
| sdc-sdc-wfd-fe | No subject alternative DNS name matching aaf-locate.pltf-onap found. | in progress
| sdc-sdc-be-config-backend | Back-off pulling image "image-registry.openshift-image-registry.svc:5000/pltf-onap/readiness:3.0.1" | in progress
| sdc-sdc-cs-config-cassandra | Statefulset cassandra-cassandra is NOT ready | in progress
| sdc-sdc-wfd-be-workflow-init | Back-off pulling image "image-registry.openshift-image-registry.svc:5000/pltf-onap/readiness:3.0.1" | in progress
| sdc-sdc-onboarding-be-cassandra-init | Back-off pulling image "image-registry.openshift-image-registry.svc:5000/pltf-onap/readiness:3.0.1" | in progress
| sdc-sdc-fe | No Entries found for 'https://aaf-locate.pltf-onap:8095/locate/pltf-onap.org.osaaf.aaf.cm:2.1' | in progress
| sdc-sdc-wfd-be | No Entries found for 'https://aaf-locate.pltf-onap:8095/locate/pltf-onap.org.osaaf.aaf.cm:2.1' | in progress
cassandra | cassandra-cassandra | Liveness probe failed: command timed out Exec lifecycle hook ([/bin/sh -c PID=$(pidof java) && kill $PID && while ps -p $PID > /dev/null; do sleep 1; done]) for Container "cassandra" in Pod "cassandra-cassandra-0_pltf-onap(6f44a9f5-aae8-419d-bd8f-dbc9a739f065)" failed - error: command '/bin/sh -c PID=$(pidof java) && kill $PID && while ps -p $PID > /dev/null; do sleep 1; done' exited with 137: , message: "" | in progress
policy | policy-policy-apex-pdp-0 | MountVolume.SetUp failed for volume "aaf-agent-certs" : configmap "policy-cert-wrapper-certs" not found | in progress
| policy-policy-api-78cbdb6c8c-n72lr | policy-policy-galera-config has not succeeded yet | in progress
| policy-policy-distribution-f598fb5c7-zfkh8 | MountVolume.SetUp failed for volume "aaf-agent-certs" : configmap "policy-cert-wrapper-certs" not found | in progress
| policy-policy-drools-pdp-0 | MountVolume.SetUp failed for volume "aaf-agent-certs" : configmap "policy-cert-wrapper-certs" not found | in progress
| policy-policy-galera-config-fk8rx |  | in progress
| policy-policy-galera-config-j7kc4 |  | in progress
| policy-policy-galera-config-jrjzt |  | in progress
| policy-policy-galera-config-mjtwh |  | in progress
| policy-policy-galera-config-x948l |  | in progress
| policy-policy-mariadb-0 | 0/23 nodes are available: 10 Insufficient cpu, 13 node(s) didn't match node selector. | in progress
| policy-policy-pap-775c7d78db-z5486 | policy-policy-galera-config has not succeeded yet | in progress
| policy-policy-xacml-pdp-7f8b6fccf-q7x5j |  | in progress
Common | logConfiguration - |  | secret created
| readinessCheck |  | secret created
| cmpv2Config |  | secret created
| cert-wrapper |  | secret created
| common |  | secret created
| certInitializer |  | secret created
| serviceAccount |  | N/A
| mariadb-galera |  | in progress
| mongo |  | in progress
| etcd |  | in progress
| dgbuilder | Invalid value: 30228: provided port is already allocated | in progress
| network-name-gen | Error: secret "network-mariadb-galera-db-root-password" not found | in progress
| music | music-music-cassandra-job-config has not succeeded yet | in progress
| mariadb-init | CreateContainerConfigError | in progress
| elasticsearch | Error: Secret "elasticsearch-certInitializer1-deployer-creds" is invalid: metadata.name: Invalid value: "elasticsearch-certInitializer1-deployer-creds": a DNS-1123 subdomain must consist of lower case alphanumeric characters, '-' or '.', and must start and end with an alphanumeric character (e.g. 'example.com', regex used for validation is '[a-z0-9]([-a-z0-9]*[a-z0-9])?(\.[a-z0-9]([-a-z0-9]*[a-z0-9])?)*') | in progress
| cassandra | Liveness probe failed: command timed out | in progress
| postgres | N/A | in progress

## pod-issues
NAME | READ | STATUS | Error | Resolution
aaf-aaf-cass-6f75cbbf65-88g6m | 2021-01-01 | Running
aaf-aaf-cm-7cfd74dbd9-b6cq7 | 2021-01-01 | Running
aaf-aaf-fs-5b4b84698c-8hlv9 | 0/1 | CrashLoopBackOff | http://10.131.43.181:10443/v1/sms/quorum/status
aaf-aaf-gui-76d76c445b-djkln | 2021-01-01 | Running
aaf-aaf-locate-5944465795-mbxq6 | 2021-01-01 | Running
aaf-aaf-oauth-fd7c47579-4lb2d | 2021-01-01 | Running
aaf-aaf-service-bcf8c8444-z69js | 2021-01-01 | Running
aaf-aaf-sms-95bdc5cb9-jv49k | 0/1 | CrashLoopBackOff | org.onap.aaf.misc.env.APIException: Cannot connect to 'https://aaf-locate.pltf-onap:8095/configure/aaf-sms@aaf-sms.onap.org/aaf' (Root URI: 'https://aaf-locate.pltf-onap:8095') No subject alternative DNS name matching aaf-locate.pltf-onap found.
aaf-aaf-sms-quorumclient-0 | 2021-01-01 | Running
aaf-aaf-sms-quorumclient-1 | 2021-01-01 | Running
aaf-aaf-sms-quorumclient-2 | 2021-01-01 | Running
aaf-aaf-sms-vault-0 | 2021-02-02 | Running
aaf-aaf-sshsm-distcenter-qk7nd | 0/1 | Completed
aaf-aaf-sshsm-testca-rgfrc | 0/1 | Completed
aai-aai-babel-747f65894-mzfb9 | 2021-02-02 | Running
aai-aai-bfb674b4c-ns9gk | 0/1 | Init:0/1
aai-aai-data-router-766f5c944b-z59mq | 2021-02-02 | Running
aai-aai-elasticsearch-5898c995f-7v2fw | 0/1 | CrashLoopBackOff | error: Unrecognized VM option 'UseConcMarkSweepGC' Error: Could not create the Java Virtual Machine. Error: A fatal exception has occurred. Program will exit. | changed resource as per customer suggestion.
aai-aai-graphadmin-create-db-schema-477vx | 0/1 | Init:Error
aai-aai-graphadmin-create-db-schema-525v9 | 0/1 | Init:Error |  |  | cpu: 200m
aai-aai-graphadmin-create-db-schema-5hff4 | 0/1 | Init:Error |  |  | memory: 512Mi
aai-aai-graphadmin-create-db-schema-7shnp | 0/1 | Init:Error
aai-aai-graphadmin-create-db-schema-8kr4j | 0/1 | Init:Error
aai-aai-graphadmin-create-db-schema-9r8v9 | 0/1 | Init:Error
aai-aai-graphadmin-create-db-schema-9xwv5 | 0/1 | Init:Error
aai-aai-graphadmin-create-db-schema-hvbhp | 0/1 | Init:Error
aai-aai-graphadmin-create-db-schema-kczf5 | 0/1 | Init:Error
aai-aai-graphadmin-create-db-schema-khcsj | 0/1 | Init:Error
aai-aai-graphadmin-create-db-schema-nb2xx | 0/1 | Init:Error
aai-aai-graphadmin-create-db-schema-qd2sl | 0/1 | Init:Error
aai-aai-graphadmin-create-db-schema-s4wks | 0/1 | Init:Error
aai-aai-graphadmin-create-db-schema-t8q29 | 0/1 | Init:Error
aai-aai-graphadmin-create-db-schema-v7qz6 | 0/1 | Init:Error
aai-aai-graphadmin-f7bfbc86d-rmrkj | 0/2 | Init:0/1
aai-aai-modelloader-5497c59b5f-44nvp | 2021-02-02 | Running
aai-aai-resources-7b8d897b9f-l4985 | 0/2 | Init:0/1
aai-aai-schema-service-5db9b954-rpbpt | 2021-02-02 | Running
aai-aai-search-data-65d76d4fb4-f987f | 2021-02-02 | Running
aai-aai-sparky-be-5bffb6c68-vwrgm | 0/2 | Init:0/1
aai-aai-traversal-855b46898c-rrv8m | 0/2 | Init:0/1
appc-appc-cdt-86798bc475-jlfjw | 2021-01-01 | Running
appc-appc-db-0 | 2021-01-01 | Running
appc-appc-dgbuilder-6ff46b8b65-zzvnt | 0/1 | Init:CrashLoopBackOff
cassandra-cassandra-0 | 0/1 | Running
cds-cds-blueprints-processor-b8f85c874-cknxk | 0/1 | Pending
cds-cds-blueprints-processor-b8f85c874-rcpfw | 0/1 | Pending
cds-cds-blueprints-processor-b8f85c874-vk5gx | 0/1 | Pending
cds-cds-command-executor-c8668c85c-vj4cp | 0/1 | Pending
cds-cds-db-0 | 2021-01-01 | Running
cds-cds-py-executor-b69ddd8f8-g7v7z | 0/1 | Pending
cds-cds-sdc-listener-5b996658-bb7j6 | 0/1 | Init:0/1
cds-cds-ui-7f947cc988-dhwwg | 2021-01-01 | Running
cli-cli-6b5dd7bf54-fl244 | 2021-01-01 | Running
contrib-ejbca-8874dcf4b-j5bgg | 0/1 | Init:CrashLoopBackOff
contrib-ejbca-config-config-job-9svqn | 0/1 | CreateContainerConfigError
contrib-netbox-app-cc69b9b8d-nb4mr | 0/1 | Pending
contrib-netbox-app-provisioning-2jktf | 0/1 | Init:Error
contrib-netbox-app-provisioning-dpmms | 0/1 | Init:Error
contrib-netbox-app-provisioning-kpxj6 | 0/1 | Init:Error
contrib-netbox-app-provisioning-rd4dm | 0/1 | Init:Error
contrib-netbox-nginx-75b5dfc984-hh29p | 0/1 | Pending
contrib-netbox-postgres-5b96749799-zlqpg | 2021-01-01 | Running
dcaegen2-dcae-bootstrap-655cf5b8bc-r6c2t | 0/1 | Init:ImagePullBackOff | changed the image url
dcaegen2-dcae-config-binding-service-86c8955977-44ff6 | 0/4 | Init:0/2
dcaegen2-dcae-dashboard-64d876d699-5xchj | 0/2 | Init:0/2
dcaegen2-dcae-deployment-handler-86dfcf97b8-trt2j | 0/2 | Init:0/3
dcaegen2-dcae-healthcheck-67848b47f7-h2pgx | 2021-01-01 | Running
dcaegen2-dcae-inventory-api-7b54f8b996-t6vgf | 0/2 | Init:ImagePullBackOff
dcaegen2-dcae-mongo-0 | 0/1 | Pending
dcaegen2-dcae-policy-handler-5447658d-hlv4d | 0/2 | Init:0/3
dcaegen2-dcae-servicechange-handler-546bbbd95c-chf2q | 0/1 | Init:0/2
dmaap-dmaap-bc-65d4bf85cb-ktsz6 | 0/1 | Init:0/6
esr-esr-gui-5cd77f7fc-2qbg7 | 2021-01-01 | Running
esr-esr-server-6844fc8469-zgjrh | 2021-02-02 | Running
etcd-etcd-0 | 2021-01-01 | Running
mariadb-mariadb-galera-0 | 2021-01-01 | Running
mariadb-mariadb-init-config-job-6m4pd | 0/1 | CreateContainerConfigError
modeling-modeling-etsicatalog-84bf7965bc-z78mf | 0/2 | Init:CrashLoopBackOff
modeling-modeling-etsicatalog-config-job-bd22m | 0/1 | CreateContainerConfigError
mongo-mongo-0 | 2021-01-01 | Running
msb-kube2msb-768d9c5b96-26tf5 | 2021-01-01 | Running
msb-msb-consul-68bf8d8c85-pnf7t | 2021-01-01 | Running
msb-msb-discovery-6d77b64784-2hrts | 2021-02-02 | Running
msb-msb-eag-58cd76cb64-7pmg7 | 2021-02-02 | Running
msb-msb-iag-68ffcf84db-lm7v8 | 2021-02-02 | Running
multicloud-multicloud-6b9fb9d7b8-7wh4w | 2021-02-02 | Running
multicloud-multicloud-azure-684b757b8b-v9mmz | 2021-02-02 | Running
multicloud-multicloud-fcaps-7f4d6c79c8-bcsmz | 2021-03-03 | Running
multicloud-multicloud-k8s-5c8474ff64-2255z | 2021-02-02 | Running
multicloud-multicloud-k8s-etcd-0 | 2021-01-01 | Running
multicloud-multicloud-k8s-mongo-0 | 2021-01-01 | Running
multicloud-multicloud-pike-68db6f465f-lsl2v | 2021-02-02 | Running
multicloud-multicloud-starlingx-776b9dfcff-zdzfh | 2021-03-03 | Running
multicloud-multicloud-vio-54f8bfd9d7-2vcw2 | 2021-02-02 | Running
multicloud-multicloud-windriver-6d5cb56555-dnw2d | 2021-03-03 | Running
network-nengdb-init-config-job-nxd2q | 0/1 | CreateContainerConfigError
network-network-name-gen-678bd466b7-jfd4b | 0/1 | Init:0/1
oof-cmso-db-0 | 0/1 | CreateContainerConfigError
oof-cmso-db-config-config-job-2ccz6 | 0/1 | Init:Error
oof-cmso-db-config-config-job-2ts5c | 0/1 | Init:Error
oof-cmso-db-config-config-job-2v6nr | 0/1 | Init:Error
oof-cmso-db-config-config-job-55ttg | 0/1 | Init:Error
oof-cmso-db-config-config-job-5bgh7 | 0/1 | Init:Error
oof-cmso-db-config-config-job-6t2vq | 0/1 | Init:Error
oof-cmso-db-config-config-job-6ts69 | 0/1 | Init:Error
oof-cmso-db-config-config-job-bbzw7 | 0/1 | Init:Error
oof-cmso-db-config-config-job-bmb6l | 0/1 | Init:Error
oof-cmso-db-config-config-job-ccnvp | 0/1 | Init:Error
oof-cmso-db-config-config-job-hk52n | 0/1 | Init:Error
oof-cmso-db-config-config-job-jbqc4 | 0/1 | Init:Error
oof-cmso-db-config-config-job-njcmf | 0/1 | Init:Error
oof-cmso-db-config-config-job-p8664 | 0/1 | Init:Error
oof-cmso-db-config-config-job-vpn2j | 0/1 | Init:Error
oof-cmso-db-config-config-job-w7sng | 0/1 | Init:Error
oof-music-7dfd66cdb4-p9x4n | 0/1 | Init:0/2
oof-music-cassandra-0 | 0/1 | Running
oof-music-cassandra-job-config-59vn5 | 0/1 | Init:ImagePullBackOff
oof-oof-8d9996667-965nv | 0/1 | Init:0/2
oof-oof-cmso-optimizer-7cb5658465-dx28b | 0/1 | Init:0/4
oof-oof-cmso-service-7b9c958495-p872h | 0/3 | Init:0/4
oof-oof-cmso-ticketmgt-5cb5dd68bb-58t72 | 0/1 | Init:0/1
oof-oof-cmso-topology-85869658f8-jnp27 | 0/1 | Init:0/1
oof-oof-has-api-797dddf445-s867k | 0/2 | Init:0/3
oof-oof-has-controller-6f579bdfcf-kbrgq | 0/1 | Init:0/3
oof-oof-has-data-86b485ddcc-flb7h | 0/1 | Init:0/4
oof-oof-has-reservation-dc5cc9c99-wsdtp | 0/1 | Init:0/4
oof-oof-has-solver-64759c8574-dzbtq | 0/1 | Init:0/4
policy-policy-apex-pdp-0 | 0/1 | Init:0/3
policy-policy-api-7db6cc7684-dtkjc | 0/1 | Init:0/4
policy-policy-distribution-59456d46c-xkhbg | 0/1 | Init:ImagePullBackOff
policy-policy-drools-pdp-0 | 0/1 | Init:0/3
policy-policy-galera-config-26l4r | 0/1 | Init:Error
policy-policy-galera-config-bqrnt | 0/1 | Init:Error
policy-policy-galera-config-jcxnx | 0/1 | Init:Error
policy-policy-galera-config-tcckx | 0/1 | Init:Error
policy-policy-galera-config-wbgzz | 0/1 | Init:Error
policy-policy-mariadb-0 | 0/1 | CreateContainerConfigError
policy-policy-pap-968d55854-llphd | 0/1 | Init:0/4
policy-policy-xacml-pdp-77cfc4c8b7-t9nhn | 0/1 | Init:0/4
portal-portal-app-596b57cb47-fkldr | 0/2 | Init:0/4
portal-portal-cassandra-65bf6f459d-j2tbh | 0/1 | CrashLoopBackOff
portal-portal-db-5bc9ff78cd-m5jzh | 2021-01-01 | Running
portal-portal-db-config-kts2s | 0/2 | Completed
portal-portal-sdk-7696f6d865-xhnc5 | 0/2 | Init:3/4
portal-portal-widget-8c697ff5d-5fg8n | 0/1 | Init:ImagePullBackOff
sdc-sdc-be-684464d5d-xwq2h | 0/2 | Init:CrashLoopBackOff
sdc-sdc-be-config-backend-cs7c2 | 0/1 | Init:Error
sdc-sdc-be-config-backend-gjtzr | 0/1 | Init:Error
sdc-sdc-be-config-backend-hnlch | 0/1 | Init:Error
sdc-sdc-be-config-backend-m8n8p | 0/1 | Init:Error
sdc-sdc-be-config-backend-mbsx2 | 0/1 | Init:Error
sdc-sdc-be-config-backend-nmmz4 | 0/1 | Init:Error
sdc-sdc-be-config-backend-p5hdn | 0/1 | Init:Error
sdc-sdc-be-config-backend-phbn7 | 0/1 | Init:Error
sdc-sdc-be-config-backend-rqqv7 | 0/1 | Init:Error
sdc-sdc-be-config-backend-x2r7q | 0/1 | Init:Error
sdc-sdc-be-config-backend-xgrs6 | 0/1 | Init:Error
sdc-sdc-be-config-backend-zt8pn | 0/1 | Init:Error
sdc-sdc-cs-config-cassandra-589st | 0/1 | Init:Error
sdc-sdc-cs-config-cassandra-74jl8 | 0/1 | Init:Error
sdc-sdc-cs-config-cassandra-74mjm | 0/1 | Init:Error
sdc-sdc-cs-config-cassandra-7lgxc | 0/1 | Init:Error
sdc-sdc-cs-config-cassandra-8hlv7 | 0/1 | Init:Error
sdc-sdc-cs-config-cassandra-9gkwz | 0/1 | Init:Error
sdc-sdc-cs-config-cassandra-crq8t | 0/1 | Init:Error
sdc-sdc-cs-config-cassandra-f6hhg | 0/1 | Init:Error
sdc-sdc-cs-config-cassandra-gw8rt | 0/1 | Init:Error
sdc-sdc-cs-config-cassandra-hd65q | 0/1 | Init:Error
sdc-sdc-cs-config-cassandra-m2gfq | 0/1 | Init:Error
sdc-sdc-cs-config-cassandra-t7qf6 | 0/1 | Init:Error
sdc-sdc-cs-config-cassandra-vm45k | 0/1 | Init:Error
sdc-sdc-cs-config-cassandra-wnn8f | 0/1 | Init:Error
sdc-sdc-fe-7865f9b7f7-jq484 | 0/2 | Init:0/4
sdc-sdc-onboarding-be-cassandra-init-45mnn | 0/1 | Init:Error
sdc-sdc-onboarding-be-cassandra-init-58l4l | 0/1 | Init:Error
sdc-sdc-onboarding-be-cassandra-init-66xb6 | 0/1 | Init:Error
sdc-sdc-onboarding-be-cassandra-init-7948r | 0/1 | Init:Error
sdc-sdc-onboarding-be-cassandra-init-9k6b9 | 0/1 | Init:Error
sdc-sdc-onboarding-be-cassandra-init-ddv5j | 0/1 | Init:Error
sdc-sdc-onboarding-be-cassandra-init-gtm5v | 0/1 | Init:Error
sdc-sdc-onboarding-be-cassandra-init-jmnqv | 0/1 | Init:Error
sdc-sdc-onboarding-be-cassandra-init-lqmz5 | 0/1 | Init:Error
sdc-sdc-onboarding-be-cassandra-init-m2gq4 | 0/1 | Init:Error
sdc-sdc-onboarding-be-cassandra-init-m4zfp | 0/1 | Init:Error
sdc-sdc-onboarding-be-cassandra-init-m82hc | 0/1 | Init:Error
sdc-sdc-onboarding-be-cassandra-init-q8brk | 0/1 | Init:Error
sdc-sdc-onboarding-be-cassandra-init-sps7j | 0/1 | Init:Error
sdc-sdc-onboarding-be-cassandra-init-t7z5l | 0/1 | Init:Error
sdc-sdc-onboarding-be-cassandra-init-tpfhl | 0/1 | Init:Error
sdc-sdc-onboarding-be-cassandra-init-xvcjp | 0/1 | Init:Error
sdc-sdc-wfd-be-5b896b78c7-j52lf | 0/1 | Init:0/3
sdc-sdc-wfd-be-workflow-init-4vdmd | 0/1 | Init:Error
sdc-sdc-wfd-be-workflow-init-57wq7 | 0/1 | Init:Error
sdc-sdc-wfd-be-workflow-init-b4zxc | 0/1 | Init:Error
sdc-sdc-wfd-be-workflow-init-bzlxk | 0/1 | Init:Error
sdc-sdc-wfd-be-workflow-init-c5kwq | 0/1 | Init:Error
sdc-sdc-wfd-be-workflow-init-d9rdv | 0/1 | Init:Error
sdc-sdc-wfd-be-workflow-init-llm25 | 0/1 | Init:Error
sdc-sdc-wfd-be-workflow-init-m2cnz | 0/1 | Init:Error
sdc-sdc-wfd-be-workflow-init-rjsdg | 0/1 | Init:Error
sdc-sdc-wfd-be-workflow-init-s5bcl | 0/1 | Init:Error
sdc-sdc-wfd-be-workflow-init-t92mk | 0/1 | Init:Error
sdc-sdc-wfd-be-workflow-init-vzrhf | 0/1 | Init:Error
sdc-sdc-wfd-be-workflow-init-xgfmt | 0/1 | Init:Error
sdc-sdc-wfd-be-workflow-init-zhxwg | 0/1 | Init:Error
sdc-sdc-wfd-be-workflow-init-zxdzs | 0/1 | Init:Error
sdc-sdc-wfd-be-workflow-init-zxq7d | 0/1 | Init:Error
sdc-sdc-wfd-fe-74947b966f-v7qcz | 0/2 | Init:0/4
so-so-754b66f5fd-q7r8b | 2021-02-02 | Running
so-so-bpmn-infra-55569d7ccd-5z994 | 2021-02-02 | Running
so-so-catalog-db-adapter-5566bfc57d-rn789 | 2021-01-01 | Running
so-so-cnf-adapter-56c76b88c9-ltvlv | 2021-01-01 | Running
so-so-etsi-nfvo-ns-lcm-66565bbd55-w7xxr | 0/1 | CrashLoopBackOff
so-so-mariadb-config-job-kx4vq | 0/1 | Completed
so-so-monitoring-64b7b46bd6-858rh | 0/1 | Init:ImagePullBackOff
so-so-nssmf-adapter-689844bc4f-sxlb8 | 2021-01-01 | Running
so-so-oof-adapter-d64f7cf7c-nsvnr | 2021-02-02 | Running
so-so-openstack-adapter-67b95b755f-q4dkk | 2021-02-02 | Running
so-so-request-db-adapter-6864d4778-5vbkm | 2021-01-01 | Running
so-so-sdc-controller-845dc47ff-8ln4k | 2021-02-02 | Running
so-so-sdnc-adapter-bfcf9bb57-5mf7b | 2021-02-02 | Running
so-so-vfc-adapter-58bbcc6c9f-qnsqb | 2021-01-01 | Running
so-so-vnfm-adapter-7d56c44b5f-nklvc | 0/1 | CrashLoopBackOff
test-busybox-dep-2-deploy | 0/1 | Error
uui-uui-5b4dddd95d-76nwv | 2021-01-01 | Running
uui-uui-server-6d695f8cf9-tcqlw | 2021-01-01 | Running
vid-vid-c75497cf9-8gplx | 0/2 | Init:0/1
vid-vid-galera-0 | 2021-01-01 | Running
vid-vid-galera-1 | 2021-01-01 | Running
vid-vid-galera-2 | 2021-01-01 | Running

## Sheet3
Component Name | Sub Component Name
cassandra
mariadb-galera
aaf
aai
appc
cds
clamp
cli
contrib
consul
dcaegen2
dcaemod
dmaap
esr
oof
msb
multicloud
nbi
policy
portal
robot
sdc
sdnc
so
uui
vfc
vid
vnfsdk
modeling
platform
a1policymanagement

## Estimated Date
COMPPONENT | SUB COMPPONENT | STATUS | ISSUE | RESOLUTION | DEPEDANCY / HELP | OWNERSHIP | PLANNED TARGET DATE
cassandra | cassandra |  |  |  | VPN | Dasrathi
mariadb-galera | mariadb-galera
aaf | aaf-aaf-cass |  |  |  |  | Vamshi
aaf | aaf-aaf-cm |  |  |  |  | Vamshi
aaf | aaf-aaf-fs |  |  |  |  | Vamshi
aaf | aaf-aaf-gui |  |  |  |  | Vamshi
aaf | aaf-aaf-locate |  |  |  |  | Vamshi
aaf | aaf-aaf-oauth |  |  |  |  | Vamshi
aaf | aaf-aaf-service |  |  |  |  | Vamshi
aaf | aaf-aaf-sms |  |  |  |  | Vamshi
aaf | aaf-aaf-sms-quorumclient |  |  |  |  | Vamshi
aaf | aaf-aaf-sms-vault |  |  |  |  | Vamshi
aaf | aaf-aaf-sshsm-distcenter |  |  |  |  | Vamshi
aaf | aaf-aaf-sshsm-testca |  |  |  |  | Vamshi
aai | aai-babel
aai | aai
aai | aai-data-router
aai | aai-elasticsearch
aai | aai-graphadmin-create-db-schema
aai | aai-graphadmin
aai | aai-modelloader
aai | aai-resources
aai | aai-schema-service
aai | aai-search-data
aai | aai-sparky-be
aai | aai-traversal
appc | appc-cdt
appc | appc-db
appc | appc-dgbuilder
cdc | cds-blueprints-processor
cdc | cds-command-executor
cdc | cds-db
cdc | cds-py-executor
cdc | cds-sdc-listener
cdc | cds-ui
cli | cli
contrib | contrib-ejbca
contrib | contrib-ejbca-config-config-job
contrib | contrib-netbox-app
contrib | contrib-netbox-app-provisioning
contrib | contrib-netbox-nginx
contrib | contrib-netbox-postgres
msb | msb-consul
dcaegen2 | dcaegen2-dcae-bootstrap
dcaegen2 | dcaegen2-dcae-config-binding-service
dcaegen2 | dcaegen2-dcae-dashboard
dcaegen2 | dcaegen2-dcae-deployment-handler
dcaegen2 | dcaegen2-dcae-healthcheck
dcaegen2 | dcaegen2-dcae-inventory-api
dcaegen2 | dcaegen2-dcae-mongo-0
dcaegen2 | dcaegen2-dcae-policy-handler
dcaegen2 | dcaegen2-dcae-servicechange-handler
dmaap | dmaap-bc
esr | esr-gui
esr | esr-server
oof | oof-cmso-db-0
oof | oof-cmso-db-config-config-job
oof | oof-music
oof | oof-music-cassandra-0
oof | oof-music-cassandra-job-config
oof | oof
oof | oof-cmso-optimizer
oof | oof-cmso-service
oof | oof-cmso-ticketmgt
oof | oof-cmso-topology
oof | oof-has-api
oof | oof-has-controller
oof | oof-has-data
oof | oof-has-reservation
oof | oof-has-solver
msb | msb-kube2msb
msb | msb-consul
msb | msb-discovery
msb | msb-eag
msb | msb-iag
multicloud | multicloud
multicloud | multicloud-azure
multicloud | multicloud-k8s
multicloud | multicloud-k8s-etcd
multicloud | multicloud-k8s-mongo
multicloud | multicloud-pike
multicloud | multicloud-starlingx
multicloud | multicloud-vio
multicloud | multicloud-windriver
policy | policy-apex-pdp
policy | policy-api
policy | policy-distribution
policy | policy-drools-pdp-0
policy | policy-galera-config
policy | policy-mariadb-0
policy | policy-pap
policy | policy-xacml-pdp
portal | portal-app |  |  |  |  | Vamshi
portal | portal-cassandra |  |  |  |  | Vamshi
portal | portal-db |  |  |  |  | Vamshi
portal | portal-db-config |  |  |  |  | Vamshi
portal | portal-sdk |  |  |  |  | Vamshi
portal | portal-widget |  |  |  |  | Vamshi
sdc | sdc-be |  |  |  |  | Vamshi
sdc | sdc-be-config-backend |  |  |  |  | Vamshi
sdc | sdc-cs-config-cassandra |  |  |  |  | Vamshi
sdc | sdc-fe |  |  |  |  | Vamshi
sdc | sdc-onboarding-be-cassandra-init |  |  |  |  | Vamshi
sdc | sdc-wfd-be |  |  |  |  | Vamshi
sdc | sdc-wfd-be-workflow-init |  |  |  |  | Vamshi
sdc | sdc-wfd-fe |  |  |  |  | Vamshi
so | so
so | so-bpmn-infra
so | so-catalog-db-adapter
so | so-cnf-adapter
so | so-etsi-nfvo-ns-lcm
so | so-mariadb-config-job
so | so-monitoring
so | so-nssmf-adapter
so | so-oof-adapter
so | so-openstack-adapter
so | so-request-db-adapter
so | so-sdc-controller
so | so-sdnc-adapter
so | so-vfc-adapter
so | so-vnfm-adapter
uui | uui
uui | uui-server
vid | vid
vid | vid-galera-0
modeling | modeling-etsicatalog
modeling | modeling-etsicatalog-config-job